HomeHub

Technical Execution Plan

Phase 0 → V2.0

February 2026

# 1. Document Purpose

This document serves as the single source of truth for all development work from the current MVP through V2.0 release. It is designed to be consumed both by the developer and by Claude Code agents executing tasks. Every section includes acceptance criteria, dependencies, and agent-assignable task breakdowns.

# 2. Current State Summary

| Dimension | Status |
| --- | --- |
| Framework | React (Vite) + TypeScript + Tailwind CSS |
| Backend | Supabase (Auth, Postgres DB, Storage) |
| Users | Multi-user with household concept |
| Persistence | localStorage + Supabase (hybrid) |
| Hubs Built | Shopping & Gear, Home Tasks, Vouchers & Reservations |
| Known Issues | Vouchers/Reservations dynamic card rendering unstable |
| Tests | None |
| i18n | None (English only) |
| Deployment | Web-based, not responsive, no PWA |

# 3. Execution Phases Overview

## Phase 0: Stabilization & Foundation

- 0.1  Vouchers / Bookings Separation

- 0.2  Comprehensive Test Suite (e2e, unit, manual/sanity)

- 0.3  Gmail OAuth Integration

- 0.4  Hebrew Localization (i18n)

- 0.5  Responsive Design + PWA Foundation

## Phase 1: V2.0 Feature Development

- 1.1  Bill Management (Gmail ingestion → Tasks Hub)

- 1.2  Shared Calendar & Deadlines Carousel

- 1.3  Push Notifications

- 1.4  WhatsApp Agent (LLM + Function Calling)

- 1.5  Native PWA Finalization

# 4. Dependency Map

- 0.1 Vouchers Refactor → unblocks 0.2 Test Suite → gates ALL V2 work

- 0.3 Gmail OAuth → feeds directly into 1.1 Bill Management

- 0.5 PWA Foundation → required for 1.5 PWA Finalization → required for 1.3 Push Notifications

- 0.1 Vouchers Refactor → enables 1.2 Calendar Carousel (voucher expiry data)

- 1.1 Bill Management → triggers 1.3 Push Notifications (bill alerts)

- All hubs stable → prerequisite for 1.4 WhatsApp Agent

# 5. Phase 0 — Detailed Task Breakdown

## 5.1 Vouchers / Bookings Separation

Goal: Decouple the polymorphic Voucher/Reservation model into two distinct data models with static card templates, eliminating rendering instability.

### Data Model Split

- Create separate Supabase tables: vouchers and reservations

- Voucher fields: id, name, value, issuer, expiry_date, code, image_url, notes, household_id, created_by

- Reservation fields: id, name, event_date, time, address, image_url, notes, household_id, created_by

- Write migration script from current polymorphic table

- Add RLS policies for household-level access

### Static Card Components

- Replace dynamic card renderer with VoucherCard.tsx (shows: name, value, issuer, expiry)

- Create ReservationCard.tsx (shows: name, date/time, address)

- Remove all conditional rendering logic causing instability

### Acceptance Criteria

- Zero dynamic type-checking in card rendering

- Both card types render correctly in grid view

- Existing data migrated without loss

- Modal detail view works for both types

## 5.2 Comprehensive Test Suite

Goal: Establish full test coverage before any V2 work begins.

| Layer | Tool | Scope |
| --- | --- | --- |
| Unit Tests | Vitest | Utility functions, hooks, context logic, categorization |
| Component Tests | Vitest + RTL | Cards, forms, modals, bubbles |
| Integration Tests | Vitest + RTL | Hub flows, list management, CRUD |
| E2E Tests | Playwright | Full user journeys across all hubs |
| Manual/Sanity | Checklist | Pre-release regression checklist |

### Acceptance Criteria

- All tests pass in CI

- Unit coverage >80% on business logic

- E2E covers all critical user journeys

- Sanity checklist document created and versioned

## 5.3 Gmail OAuth Integration

Goal: Replace current independent OAuth with standard Gmail OAuth 2.0, scoped to metadata-only read access.

- Register app in Google Cloud Console with gmail.readonly scope

- Implement OAuth 2.0 authorization code flow

- Store refresh tokens securely in Supabase (encrypted)

- Build connection UI in Settings: Connect/Disconnect with status indicator

- Create Supabase Edge Function: gmail-fetch for email metadata access

### Acceptance Criteria

- User connects Gmail with one click

- Tokens stored securely, auto-refresh working

- Email metadata accessible via Edge Function

- Disconnect works cleanly

## 5.4 Hebrew Localization (i18n)

Goal: Full RTL Hebrew language support throughout the application.

- Install and configure react-i18next + i18next

- Extract all hardcoded strings into translation keys

- Add dir="rtl" attribute toggling on HTML element

- Replace all directional Tailwind classes (ml/mr) with logical properties (ms/me)

- Translate all UI strings, context keywords, bubble labels, and error messages

- Add language toggle in Settings (English / Hebrew)

### Acceptance Criteria

- Language toggle works without page reload

- RTL layout renders correctly across all views

- No hardcoded strings remain in components

- Context engine works with Hebrew keywords

## 5.5 Responsive Design + PWA Foundation

Goal: Fix responsive issues across devices and lay PWA groundwork.

- Audit and fix on: iPhone SE, iPhone 14, Pixel 7, iPad, Desktop

- Fix breakpoints, grid layouts, touch targets (min 44x44px), font scaling, overflow

- Create manifest.json with app icons, theme color (#630606), standalone mode

- Register service worker via vite-plugin-pwa (basic cache strategy)

- Offline fallback page

### Acceptance Criteria

- App renders correctly on all target devices

- App installable to home screen (Android + iOS)

- Standalone mode works (no browser chrome)

- Basic offline fallback shows when disconnected

# 6. Phase 1 — V2.0 Feature Development

## 6.1 Bill Management

Goal: Automated bill ingestion from Gmail into a dedicated Bills list in Home Tasks Hub.

Depends on: 0.3 Gmail OAuth

### Architecture

Gmail API → Supabase Edge Function (scan/extract) → LLM Agent (classify + extract) → Bills list in Tasks Hub

### Key Components

- Initial 90-day scan engine with LLM vendor identification

- Review screen: approve/reject vendors, sample subjects, manual add

- Data extraction: amount, due date, billing period, payment link, PDF

- Deduplication via composite key: vendor_name + billing_period

- Task cards with inline amount/date, Pay Now deep link, View Invoice

- Opt-in modal with disclaimer about potential errors

## 6.2 Shared Calendar & Deadlines Carousel

Goal: Top-of-dashboard carousel showing bills, expiring vouchers, urgent tasks, and personal calendar events.

Depends on: 0.1 Vouchers Refactor, 1.1 Bill Management

- Horizontal scrollable carousel at top of Home Hub

- Card types: Bills, Vouchers, Tasks Badge, Personal Calendar

- Optional Google Calendar integration (Today + Tomorrow, private events only)

- Visual distinction: Home vs Personal labels on each card

## 6.3 Push Notifications

Goal: Real-time contextual alerts with privacy-preserving lock screen content.

Depends on: 0.5 PWA (Service Worker), 1.1 Bill Management

| Topic | Lock Screen | Quick Action | Deep Link |
| --- | --- | --- | --- |
| Bills | A new household bill has arrived | Pay Now | Bill Task Card |
| Urgent Tasks | You have urgent tasks pending | View Tasks | Urgent tasks list |
| Vouchers | Business + Amount + Urgency | Redeem | Voucher detail |
| Events | Event + Time + Location | Open Ticket | Booking detail |

- Quiet Hours with queue: notifications delivered in batch when window ends

- Category toggles: Bills, Tasks, Vouchers — independent on/off

- Daily digest at 08:00 (user-configurable)

## 6.4 WhatsApp Agent

Goal: LLM-powered bot in household WhatsApp group that detects intent and manages lists.

### Architecture

WhatsApp Business API → Webhook → Supabase Edge Function → LLM (Claude API) with Function Calling → HomeHub DB

### Agent Tools

- search_lists() — queries existing lists in Shopping and Tasks hubs

- add_item_to_list() — appends item to specified list

- create_new_list() — creates new list when no match found

### Confirmation Loop

- Stage A: Execute + confirm with Confirm/Cancel buttons

- Stage B: On cancel → offer redirect to different list

- Stage C: Resolve (redirect or abandon)

### Safety & Privacy

- Sensitive keyword detection triggers proactive privacy reminder

- Voice notes rejected with friendly message

- Media acknowledged without processing

- Agent personality: 60% friendly / 40% formal

## 6.5 Native PWA Finalization

Goal: Complete PWA experience with full offline capability, background sync, and platform parity.

- Full offline support with cached app shell + data

- Background sync: queue mutations when offline, sync on reconnect

- Code splitting by hub, image optimization (WebP, lazy loading)

- Target: Lighthouse PWA >90, Performance >85

- iOS and Android feature parity

# 7. Multi-Agent Workflow Guide

Instead of one Claude Code session doing everything sequentially, you create specialized agents with focused responsibilities.

| Agent Role | Responsibility | Works On |
| --- | --- | --- |
| Architect | Schema, data models, migrations, Edge Functions | Supabase, src/lib/, supabase/ |
| Frontend | Components, pages, styling, responsive | src/components/, src/pages/ |
| Integration | OAuth, APIs, WhatsApp, Gmail, Calendar | src/lib/api/, supabase/functions/ |
| QA | Tests, coverage, sanity, bug verification | tests/, e2e/ |

## Parallelization Map

Parallel Group A: 0.1 Vouchers Refactor + 0.4 i18n Setup + 0.5 Responsive Audit

Sequential: 0.2 Test Suite (after 0.1) → 0.3 Gmail OAuth (blocks 1.1)

Parallel Group B: 1.1 Bill Management + 1.2 Calendar Carousel + 1.5 PWA Finalization

Sequential: 1.3 Push Notifications (after 1.1 + 1.5) → 1.4 WhatsApp Agent (after all stable)

# 8. Milestone Timeline

| Milestone | Tasks | Duration | Gate |
| --- | --- | --- | --- |
| M0: Stabilize | 0.1 Vouchers + 0.5 Responsive | 1–2 weeks | Cards render on all devices |
| M1: Test & i18n | 0.2 Tests + 0.4 Hebrew | 1–2 weeks | All tests green, Hebrew works |
| M2: Gmail | 0.3 Gmail OAuth | 1 week | Gmail connected, emails accessible |
| M3: Bills | 1.1 Bill Management | 2–3 weeks | Bills auto-extracted and displayed |
| M4: Calendar + PWA | 1.2 Carousel + 1.5 PWA | 2 weeks | Carousel live, app installable |
| M5: Notifications | 1.3 Push Notifications | 1–2 weeks | Notifications on all platforms |
| M6: WhatsApp | 1.4 WhatsApp Agent | 2–3 weeks | Agent manages lists via group |

Total estimated: 10–15 weeks

# 9. Risk Register

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Gmail API quota limits | Bill scanning throttled | Batch scans, cache results |
| WhatsApp Business API cost | Agent launch delayed | Start with sandbox, apply early |
| iOS PWA push limitations | No notifications on iOS | Verify iOS 16.4+, fallback to in-app |
| Hebrew bill extraction accuracy | Wrong amounts | Vendor validation + human review flag |
| Multi-agent merge conflicts | Code breakage | Clear file ownership, frequent merges |
| Scope creep | Timeline slips | Strict acceptance criteria per milestone |